## 1- SMART Tracking Dasboard
SMART Tracking Dashboard
KPI's
| ID | Milestone | Status | Progress | Priority | Next Action | Project Health
| M1 | Foundation | Complete | 100% | High | Closed
| M2 | Story | In Progress | 80% | High | Complete Story Script | 🟢 On Track
| M3 | Branding | Not Started | 20% | High | Create Brand Kit | 🟡 Attention
| M4 | Website | Not Started | 0% | High | Buy Domain | 🔴 Critical
| M5 | Community | Not Started | 0% | Medium | Define Registration Form
| M6 | Board Game | Not Started | 0% | Medium | Define Rules
| M7 | Launch | Not Started | 0% | Low | N/A
Overall Progress %
Current Milestone
Open Risks
Completed Deliverables
Pending Deliverables

## 2- Milestone Details
Milestone Details
Por cada milestone:
Milestone Tracker
Deliverable | Complete |  | ID | Milestone | Status | Progress % | Priority | Target Date | Owner
Thinking Blueprint | Yes |  | M1 | Foundation | Complete | 100 | High | 2026-10-01 | Raul
Mission | Yes |  | M2 | Story | In Progress | 80 | High | 2026-11-01 | Raul
Strategy | Yes |  | M3 | Branding | Not Started | 0 | High | 2026-11-01 | Raul
Process | Yes |  | M4 | Website | Not Started | 0 | High | 2026-12-01 | Raul
Action | Yes |  | M5 | Community | Not Started | 0 | Medium | 2027-01-01 | Raul
Results | Yes |  | M6 | Board Game | Not Started | 0 | Medium | 2027-02-01 | Raul
Transformation | Yes |  | M7 | Release | Not Started | 0 | High | 2027-03-01 | Raul
Community | No
Ecosystem | No
Story Script | No
| #NAME? | 80%

## 3- WBS Tracker
WBS Tracker
WBS ID | Deliverable | Parent | Status | %
2.1 | The Builder™ | Identity | Complete | 100
2.2 | Builder Manifesto™ | Identity | Complete | 100
3.2.1 | Thinking Blueprint™ | Story | Complete | 100
3.2.2 | Mission | Story | Complete | 100
3.2.3 | Strategy | Story | Complete | 100
3.2.4 | Process | Story | Complete | 100

## 4- SMART Matrix
SMART Matrix
Milestone | SMART Requirement | Completed
M2 | Thinking Blueprint | Yes
M2 | Mission | Yes
M2 | Strategy | Yes
M2 | Process | Yes
M2 | Action | Yes
M2 | Results | Yes
M2 | Transformation | Yes
M2 | Community | No
M2 | Ecosystem | No
M2 | Story Script | No
0

## 5- Roadmap
[11 empty] | TODAY: | 2026-10-24
[10 empty] | SINCE START PJ: |  | 23
Window
Milestone |  |  | Start | Finish | Duration Days | Effort Hours | Progress % | CompletedDays | Remaining Days
M1 Foundation |  |  | 2026-10-01 | 2026-10-31 | 30 | 22 | 100% | 30 | 0
| TRUE | Project Charter v1.0 |  |  |  |  | 100%
| TRUE | Project Management Plan v1.0 |  |  |  |  | 100%
| TRUE | WBS (Work Breakdown Structure) v1.0 |  |  |  |  | 100%
| TRUE | Strategic Roadmap v1.0 |  |  |  |  | 100%
| TRUE | SMART Milestone v1.0 |  |  |  |  | 100%
| TRUE | SMART Tracking Matrix v1.0 |  |  |  |  | 100%
| TRUE | Risk Register v1.0 |  |  |  |  | 100%
| TRUE | Builder Command Center Struture |  |  |  |  | 100%
| TRUE | Project Folder Structure |  |  |  |  | 100%
| TRUE | Version Control Structure |  |  |  |  | 100%
M2 Story |  |  | 2026-10-15 | 2026-11-15 | 31 | 23 | 70% | 21.7 | 9.3
| TRUE | Thinking Blueprint |  |  |  |  | 100%
| TRUE | Mission |  |  |  |  | 100%
| TRUE | Strategy |  |  |  |  | 100%
| TRUE | Process |  |  |  |  | 100%
| TRUE | Action |  |  |  |  | 100%
| TRUE | Results |  |  |  |  | 100%
| TRUE | Transformation |  |  |  |  | 100%
| FALSE | Community |  |  |  |  | 0%
| FALSE | Ecosystem |  |  |  |  | 0%
| FALSE | Story Script |  |  |  |  | 0%
M3 Branding |  |  | 2026-11-01 | 2026-11-30 | 29 | 21 | 22.22% | 6.4444 | 22.5556
| FALSE | Logo |  |  |  |  | 0%
| FALSE | Color Palette |  |  |  |  | 0%
| FALSE | Typography |  |  |  |  | 0%
| FALSE | Brand Guidelines |  |  |  |  | 0%
| FALSE | Poster |  |  |  |  | 0%
| FALSE | Infographic Set |  |  |  |  | 0%
M4 Website |  |  | 2026-11-15 | 2026-12-31 | 46 | 38 | 22.22% | 10.2222 | 35.7778
| TRUE | Domain |  |  |  |  | 100%
| TRUE | Hosting |  |  |  |  | 100%
| FALSE | Homepage |  |  |  |  | 0%
| FALSE | About (Our Story) |  |  |  |  | 0%
| FALSE | Builder Manifesto |  |  |  |  | 0%
| FALSE | Contact |  |  |  |  | 0%
M5 Community |  |  | 2027-01-01 | 2027-01-31 | 30 | 22 | 0% | 0 | 30
| FALSE | Registration Form |  |  |  |  | 0%
| FALSE | Newsletter |  |  |  |  | 0%
| FALSE | Communication Channel |  |  |  |  | 0%
| FALSE | First 10 Builders |  |  |  |  | 0%
M6 Board Game |  |  | 2027-01-15 | 2027-02-28 | 44 | 36 | 0% | 0 | 44
| FALSE | Board |  |  |  |  | 0%
| FALSE | Rules |  |  |  |  | 0%
| FALSE | Cards |  |  |  |  | 0%
| FALSE | Dice |  |  |  |  | 0%
| FALSE | Prototype |  |  |  |  | 0%
| FALSE | Play Test |  |  |  |  | 0%
| FALSE | Copyright |  |  |  |  | 0%
M7 Release |  |  | 2027-02-15 | 2027-03-15 | 28 | 20 | 0%
| FALSE | Release Date
182
Start Date: |  |  | 46296
Finish Date: |  |  | 46461
jijahb - pagina

## 6- Risks
Risk Register
ID | Risk | Probability | Impact | Score | Response
R1 | Scope Creep | High | High | 9 | Focus on v1
R2 | Too Many Ideas | High | Medium | 6 | Freeze Scope
R3 | Time Constraints | Medium | Medium | 4 | Weekly Planning
R4 | Perfectionism | High | High | 9 | MVP First

## 7- Action Log
Action Log
Aquí es donde realmente trabajarás día a día.
Action ID | Task | Milestone | Status | Due Date
A001 | Complete Story Script | M2 | Open | 2026-11-15
A002 | Create Logo Draft | M3 | Open | 2026-11-20
A003 | Buy Domain | M4 | Open | 2026-11-25

## 8- Lessons Learned
Lessons Learned
Date | Lesson Learned | Action
2026-10-01 | Story before branding | Complete narrative first
2026-10-01 | Identity emerged before website | Prioritize message before technology

## 9- Version Control
Version Control
Version | Date | Changes
1 | 2026-10-01 | Initial PMP Package
1.1 | 2026-11-01 | Story Completed
1.2 | 2026-11-01 | Branding Added
1.3 | 2026-12-01 | Website Published

## 10- Builder CC
Builder Command Center
Think → Plan → Build → Improve → Transform
Current Milestone:
M2 - Story Completed
Current Objective:
Complete Story Script
Next Deliverable:
Storyboard
Project Completion:
30%
Next Review:
Weekly